## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
My gecko kit breaks | 3 | 70 | 210 | 2021-04-02 |  | A | Not much I can do about this other than hope. I'm not buying another one until it breaks.
Unable to implement LCD Graphics Display Properly | 70 | 20 | 1400 | 2021-04-02 |  | R | Gain full understanding of implementation EARLY (by end of week 2) and have dedicated unit test of functionality
Unable to implement reliable Capsense measure | 20 | 20 | 400 | 2021-04-02 |  | R | Dedicated unit tests to find the best implementation
Unable to implement dedicated adjustable PWM | 8 | 20 | 160 | 2021-04-02 |  | R | Dedicated unit tests to ensure proper implementation
My Capstone project takes too much of my time | 70 | 8 | 560 | 2021-04-02 | Mitigated | M | Follow the intense planning procedures in ECEN3753, watch my schedule 1 week ahead to foresee conflicts with capstone project dev and 3753 project dev work
Physics Calculations Are Very Complex | 70 | 13 | 910 | 2021-04-10 | Resolved | R | Gain full understanding of calculations, ideally during wk 3.
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100